# Project Nexus – Weekly Status Update Report

Project Name: Project Nexus
 Reporting Period: April 7 – April 13, 2026
 Prepared By: Ananya Mehta, Project Manager
 Department: Digital Transformation Office
 Version: 1.0

## Executive Summary

Project Nexus is progressing on schedule, with 78% of milestone deliverables completed for Phase 2.
 This week focused on dashboard integration testing, vendor API stabilization, and user acceptance preparation.
 Two moderate risks remain under active review related to delayed vendor documentation and incomplete training materials.

## Current Status Overview

| Workstream | Status | Progress |
| --- | --- | --- |
| Dashboard Integration | On Track | 85% Complete |
| API Vendor Connectivity | At Risk | 70% Complete |
| User Acceptance Testing Prep | On Track | 75% Complete |
| Training Documentation | Delayed | 55% Complete |

## Completed This Week

### 1. Dashboard Integration

- Finance reporting dashboard connected successfully with ERP backend

- Real-time KPI sync latency reduced from 12 sec to 4 sec

### 2. API Stabilization

- Vendor endpoint issue #342 resolved

- Authentication token refresh logic implemented

### 3. Testing Readiness

- UAT test scripts drafted for 18 scenarios

- QA signoff received for workflow validation cases

## In Progress

- Final API schema validation pending from third-party vendor

- User onboarding guide under review by training team

- Regional testing environment still awaiting deployment approval

## Key Risks Identified

### Risk 1: Vendor Documentation Delay

Issue: External vendor has not submitted final API schema guide
 Impact: May delay integration completion by 3 days
 Mitigation: Escalation initiated with vendor account manager

### Risk 2: Training Materials Incomplete

Issue: End-user manuals only 60% complete
 Impact: Could affect UAT readiness
 Mitigation: Additional technical writer assigned

## Budget Summary

| Category | Allocated | Used | Remaining |
| --- | --- | --- | --- |
| Development | ₹8,00,000 | ₹6,10,000 | ₹1,90,000 |
| Vendor Services | ₹3,50,000 | ₹2,75,000 | ₹75,000 |
| Training | ₹1,50,000 | ₹60,000 | ₹90,000 |

## Upcoming Milestones

| Milestone | Due Date | Owner |
| --- | --- | --- |
| Vendor API Final Approval | April 16, 2026 | Integration Team |
| UAT Launch | April 20, 2026 | QA Lead |
| Training Manual Completion | April 18, 2026 | Documentation Team |

## Next Week Priorities

- Complete pending API schema validation

- Finalize UAT launch checklist

- Deliver full training documentation draft

- Begin pilot testing with regional managers

## Document Metadata

Author: Ananya Mehta
 Last Updated: April 13, 2026
 Approved By: Rahul Sethi, Program Director